## Sheet1
Outcome: Empower countries to monitor and forecast priority hazards as well as generate, disseminate and use impact-based, actionable early warnings to save lives, protect property and livelihoods
Intermediary Outcome 2.4: Impact-based forecasts and warnings produced for all priority hazards. (LTG 1, 3)
Success Indicator 2.4.1: # of Members producing impact-based warnings for all priority hazards |  |  | Yes, for all priority hazards = 5; Yes, for some priority hazards=17; No=45 (based on 67 Members mostly LDCs and SIDS, Source: Pillar 2 Rapid Assessments, Mar 2025)
Success Indicator 2.4.2: # of Members with Standard Operating Procedures in place for all priority hazards |  |  | Yes, for all priority hazards = 12; Yes, for some priority hazards=14; No=41 (based on 67 Members mostly LDCs and SIDS, Source: Pillar 2 Rapid Assessments, Mar 2025)
Success Indicator 2.4.3: # of Members with 24/7 warning services |  |  | Yes= 43; No=24 (based on 67 Members mostly LDCs and SIDS, Source: Pillar 2 Rapid Assessments, Mar 2025)
Output based on WMO OP (SO 1.1, 1.2, 1.3, 1.4, 1.5, 3.1, 3.2) |  | Activities Pillar 2 Implementation Plan (Outcome 4) | WMO EW4All Roadmap Activities (28-51) | WMO Responsible | Contributors (non-WMO) | Timeframe | Progress (AOP) | Comments on Progress (AOP) | Progress Indicators (from M&E framework) | Result (Mar 2025) | Source
1.1.01 | WMO Cataloguing of Hazardous Events connected to national loss and damage reporting systems and regional based statistics developed |  | Catalogue of Hazardous events (SERCOM 1.1.01) | SERCOM, S/DMPS | UNDRR, UNDP | 2025 |  |  | 2.4.1: # of NMHS with forecasters trained in IBF methods (by hazard) | Yes, full training=2 Yes, partial training=43 None=22 | Based on 67 Members, mostly LDCs and SIDS, Source: Pillar 2 Rapid Assessments, Mar 2025
1.1.03 | Business Continuity enabled in the development of sustained MHEW services | Support that operational warning centres are maintained 24/7 by competent staff, according to national and international standards | Drafting of Business Continuity Guidance to sustain MHEWS (SERCOM 1.1.03) | SERCOM, S/DMPS |  | 2024 |  |  | 2.4.2a: # of NMHSs active in publishing CAP warnings (CAP adoption) | Completed=122 Dvpt/test mode=39 Not started=32 | WMO Secretariat (Mar 2025)
1.1.04 | All NMHSs included in the updated WMO register of alerting authorities | Populate and maintain the registry of alerting authorities | WMO-RAA Incorporated into the technical regulations; (SERCOM 1.1.04) | SERCOM, S/DRR |  | 2024 |  |  | 2.4.2b: # of NMHSs active in publishing CAP warnings (sustainability in issuing alerts) | Sustained=65 Under threshold=44 No alert=84 | SWIC 3.0, 2024
|  | Joint advocacy efforts to populate the Register of Alerting Authorities (RAA) | WMO-RAA Interface updated; (SERCOM 1.1.04) | SERCOM, S/DRR |  | 2025 |  |  | 2.4.3: # of NMHS w/ failsafe, redundancies and business continuity plan in place | Yes, in place=3 Yes, partially in place=39 No=23 | Based on 65 Members, mostly LDCs and SIDS, Source: Pillar 2 Rapid Assessments, Mar 2025
1.1.06 | Alert and warning messages reach last mile through multiple channels leveraging CAP and partnerships | Develop and maintain CAP implementation guidance for all high-impact priority hydromet hazards | CAP helpdesk prototyped and preoperational (SERCOM 1.1.13) | SERCOM, S/DMPS |  | 2024
|  | Support the implementation of CAP warnings for all priority hazards | Common Alerting Protocol (CAP) – WMO e-learning courses updated; (SERCOM 1.1.06) | SERCOM, CDP, ETR, S/DRR | ITU, IFRC | 2024
|  |  | CAP editor tool integrated into WIS 2.0 in a box; (INFCOM (1)) | SERCOM, INFCOM, S/DRR, I/WIS |  | 2024
|  |  | Training in CAP for temperature, thermal and heatwave-intensity extreme heat warnings. (SERCOM 1.1.06) | SERCOM, S/DMPS
|  |  | CAP for drought | SERCOM, S/DMPS, S/ACS |  | 2027
1.1.07 | Tools and guidance for urban multi-hazard early warning contributing to objectives on the integrated urban service;
1.1.08 | Humanitarian agencies have access to WMO Member services through the WCM |  | WMO Coordination Mechanism WMO Member and expert advice regularly available to humanitarian agencies | SERCOM, S/DMPS |  | 2024
|  |  | Training strategy and materials available (SERCOM 1.1.08) | SERCOM, S/DMPS
1.1.09 | Technical guidance supporting impact-based forecast and warning services promoted or improved (including database, tools and outreach mechanism to enable IBF more effectively) | Develop and maintain guidance on issuing warnings for high-impact priority hydromet hazards | 30.2 Training Members on Heat-Early Warning System Guidance, etc. (SERCOM 1.1.09) | CDP, SERCOM, S/DMPS, MS/ETR, S/ACS |  | 2024
|  | Develop competency frameworks for warning dissemination for all priority hazards | Impact-based Forecast and Warning Services (IBFWS) eCourse expanded to include priority hazards (SERCOM 1.1.09) | CDP, SERCOM, S/DMPS, MS/ETR |  | 2024
|  | Develop and maintain guidance on QMS for warnings of all priority hydromet hazards | IBFWS online Ecosystem established, maintained, and updated (SERCOM 1.1.09) | CDP, SERCOM, S/DMPS, MS/ETR |  | 2024
|  | Evaluate regional centres’ capability to deliver accurate, timely guidance products to assist National warning message preparation | IBFWS competencies reviewed (SERCOM 1.1.09) | CDP, SERCOM, S/DMPS |  | 2024
|  | Conduct trainings for Regional Centres on issuing warning guidance in accordance with WMO policies and standards (including CAP) and maintaining QMS for warning messages for all priority hazards | RSMCs TC are leading to developing IBF products with risk information, including impacting areas, utilities, and communities for actions (SERCOM 1.1.09) | SERCOM, S/DMPS |  | 2026
|  | Increase exchange of regional knowledge and technical expertise in warning for priority hazards among Members | Training in multi-hazard linkages between drought, dust, heatwave, fire, smoke, and flash flood. (SERCOM 1.1.09) | SERCOM, S/DMPS, S/ACS |  | 2026
1.1.10 | Guidance and training material developed to support wider use of probabilistic forecasts for warning purposes |  | Support national DRR decisions to have a synergized response to tropical cyclones (SERCOM 1.1.10) | SERCOM, S/DMPS |  | 2026
|  |  | Coordinated standard operating procedures for Tropical Cyclones at regional and national levels (SERCOM 1.1.10) | SERCOM, S/DMPS |  | 2024
1.1.11 | Technical guidance supporting interoperability to enable multi-hazard and multi-disciplinary collaboration between NMHSs and other entities.
1.1.12 | DRR-related standards and technical regulations developed |  | DRR related standards and technical regulations (SERCOM 1.1.12) | SERCOM, S/DMPS |  | 2024
1.1.13 | GMAS fully operational | Subject warnings systems to regular tests and exercises, including after-action reviews | Global Multi-hazard Alert System (GMAS) – CAP guidance updated (SERCOM 1.1.13) | SERCOM, S/DMPS | UNESCO | 2024
|  | Support the production of Warnings and advisories to necessarily and appropriately cover the priority hazards | CAP helpdesk prototyped and preoperational (SERCOM 1.1.13) | SERCOM, S/DMPS |  | 2024
|  | Support the establishment and maintenance of warnings and forecast archival process and systems | SWFP to support national – subnational decision-making in DRR and disaster response. (SERCOM 1.1.13) | SERCOM, S/DMPS |  | 2026
|  | Training on QMS for warnings of all priority hydromet hazards | SWFP develop improved guidance products as feasible with support from satellite operators and RSMCs for nowcasting (SERCOM 1.1.13) | SERCOM, INFCOM, S/DMPS |  | 2025
|  |  | SWFP regional subprogrammes (SERCOM 1.1.13) | SERCOM, S/DMPS |  | 2024
|  |  | 30.1 RSMCs TC for regional advisory products and NMCs for national forecasting and warnings (SERCOM 1.1.13) | SERCOM, S/DMPS |  | 2024
|  |  | RSMCs SWF cascade WMCs’ heat related products and indices to NMHSs as/when available (SERCOM 1.1.13) | SERCOM, S/DMPS |  | 2024
|  |  | RSMCs SWF develop specific guidance products in addition to the current hazards (SERCOM 1.1.13) | SERCOM, S/DMPS |  | 2025
|  |  | Tailored guidance products developed (SERCOM 1.1.13)Meteorological/nowcasting/ Thunderstorms/squall lines | SERCOM, RB, DMPS |  | 2026
1.2.04 | WMO technical regulations, guidance and other resources associated with the provision of weather and climate services for agriculture, energy and health |  | 30.3 Identification of potential RSMCs for heatwaves centres in product support and train the trainer for extreme heat product suite. (SERCOM 1.2.04) | SERCOM, RA, S/CS, S/ACS |  | 2024
|  |  | Training Members on National Drought EWS (SERCOM 1.2.04) | CDP, SERCOM, S/CS, S/ACS |  | 2024
|  |  | Identifications of potential RSMCs drought monitoring (SERCOM 1.2.04) | SERCOM, S/CS, S/ACS |  | 2024
|  |  | Training Members on good practices for the health and all other heat-impacted essential service sectors (SERCOM 1.2.04) | SERCOM, CDP, S/ACS |  | 2025
|  |  | WAMIS (SERCOM 1.2.04) | SERCOM, S/ACS |  | 2024
|  |  | Guidelines on communicating severity classes for warnings. Co-designed hazard/impact studies guide development of heat action plans. (SERCOM 1.2.04) | SERCOM, S/DMPS |  | 2027
|  |  | Guidelines on communicatin drought information | CDP, SERCOM, S/HWC |  | 2025
1.2.14 | Contributions to climate policy frameworks through flagship climate reports, including a socio-economic impacts component |  | Climate Change and related extremes. Annual reporting at global and regional scales (1.2.14) | SERCOM , S/CMP |  | 2027
1.2.08 | Scientific and techincal advice to Members and other stakeholders on regional climate information, forecast products and tailored products provided |  | 30-year heatwave hazard climatology for a. temperature, b. thermal indices and c. heatwave-intensity indices. (SERCOM 1.2.08) | SERCOM , S/ACS |  | 2025
|  |  | Framework for the evaluation of gaps and needs with respect to national drought forecasting and early warning systems (SERCOM 1.2.08) | SERCOM , S/ACS |  | 2025
|  |  | Training Members on developing National Drought Plans and Policies (SERCOM 1.2.08) | SERCOM, S/CS, S/ACS |  | 2025
|  |  | Guidance on Flash drought (SERCOM 1.2.18) | SERCOM, S/CS, S/ACS |  | 2025
1.3.01 | WMO technical regulations, guidance and other resources associated with hydrology and water resources services |  | 2.1 Guidance on the use of Satellite data for flood forecasting and product requirements (SERCOM 1.3.01) | SERCOM , S/HWC
|  |  | Guidelines on IBF for floods and droughts (SERCOM 1.3.01) | SERCOM, S/HWC, S/ACS |  | 2026
|  |  | Guidelines on communication for hydrological information with respect to forecasting results and related risks (SERCOM 1.3.01) | SERCOM , S/HWC |  | 2026
1.3.02 | Capacity development material developed on hydrological forecasting, integrated drought management, integrated flood management, water quality and water resources assessment |  | Training materials on the Guidelines on IBF for floods and droughts (SERCOM 1.3.02) | CDP, SERCOM, MS/ETR |  | 2027
|  |  | Training materials on Guidelines on communication for hydrological information with respect to forecasting results and related risks (SERCOM 1.3.02) | CDP, SERCOM, S/HWC |  | 2027
1.3.03 | Contributions to the 5-year goal of Early Warnings for All with available tools and inventories on hydrological forecasting and water resources management services |  | 7.2 FFGS Flash Flood Guidance System (SERCOM 1.3.03) | SERCOM , S/HWC |  | 2027
|  |  | 28.4 Inventory of models and platforms for flood forecasting (SERCOM 1.3.03) | SERCOM , S/HWC |  | 2024
|  |  | Develop an impacts catalogue, based on cataloguing of hazardous sites, for reference in assessing future risks (SERCOM 1.3.03) | SERCOM, S/DRR |  | 2027
1.3.04 | Current and future status/assessments of water resources made available at different spatial and temporal scales covering a large range of products |  | 7.3 HydroSOS Hydrological Status and Outlook System (SERCOM 1.3.04) | SERCOM , S/HWC |  | 2027
|  |  | HydroSOS (SERCOM 1.3.04) trainings and guidance | SERCOM , S/HWC |  | 2026
1.3.5 | Best practices and success stories on building partnerships on water resources management at the national and international levels developed |  | APFM HelpDesk on Integrated Flood Management (SERCOM 1.3.05) | SERCOM , S/HWC |  | 2027
|  |  | APFM Guidelines on Transboundary flood risk management (SERCOM 1.3.05) | SERCOM , S/HWC |  | 2026
|  |  | APFM Training materials on Guidelines on Transboundary flood risk management (SERCOM 1.3.05) | SERCOM , S/HWC |  | 2027
|  |  | IDMP Helpdesk on Integrated Drought Management (SERCOM 1.3.05) | SERCOM, S/HWC, S/ACS |  | 2026
|  |  | IDMP – Guidance for water use, allocation, and accounting in the Water Energy Food Ecosystems nexus (SERCOM 1.3.05) | SERCOM , S/CS |  | 2025
1.3.06 | Communities of Practice (CoPs) established on (1) End-to-End Early Warning Systems for Flood Forecasting, including guidance on emerging technologies and services for data acquisition and analysis; (2) drought management; (3) water resoures assessment (including MCH) |  | 28.3 Community of Practice on flood forecasting (SERCOM 1.3.06) | SERCOM , S/HWC |  | 2027
|  |  | Dynamic Water resources Assessment Tool (DWAT) (SERCOM 1.3.06) | SERCOM, HCP, S/HWC, MS |  | 2024
1.3.08 | WMO technical regulations, guidance and other resources associated with improving the governance and development of products and services delivery by NHS | Set policy and standards to issue warnings for all high-impact priority and compound hydromet hazards | Guiding principles for engagement of the private sector to support flood-and drought related EWS and risk management (SERCOM 1.3.08) | SERCOM, S/HWC, S/ACS |  | 2027
|  | Conduct training on warning dissemination for priority hazards | Climate and hydrological prediction services (SERCOM 1.3.08) | CDP, SERCOM, S/HWC | ITU, UNDRR | 2025
1.3.10 | (a) Regional Hydrological Centers to support capacity development at the regional level, including among their functionalities the issuing of operational flood forecasting to support Members with global and regional products and verification and (b) WMO Hydrological Centers for WRA and WRM established |  | 28.1 Establishment of Regional Hydrological Centres on flash flood under WIPPS banner (SERCOM 1.3.10) | SERCOM , S/HWC |  | 2027
1.3.15 | Outputs of - Flood Forecasting Iniative Advisory Group (FFI-AG); - Regional Hydrological Fora
1.4.03 | WMO technical regulations, guidance and other resources associated with the provision and quality management of marine meteorological and oceanographic services on a national and multinational basis (e.g. WMO-Nos 558, 471, 702, 1076, 574 and 259) |  | The application of the Competency assessment implementation (Toolkit)-progress; (SERCOM 1.4.03) | SERCOM, S/MMO |  | 2027
|  |  | Consolidation of WMO position and efforts to support members working in tsunami (SERCOM 1.4.03) | SERCOM, JCB, S/MMO |  | 2027
1.4.05 | Scientific and technical advice on appropriate met-ocean products and services to address the needs of both stakeholders and the met-ocean community, especially for addressing safety of life and protection of property at sea and along the coast, including the impacts of climate change on shipping operations |  | Marine Emergency Response Guide (SERCOM 1.4.05) |  |  | 2024
|  |  | CIFI Surge Model Intercomparison and Surge Climate (SurgeMIP); (SERCOM 1.4.05) | SERCOM, S/MMO |  | 2025
|  |  | Implementation of Iridium SafetyCast across all METAREAS (SERCOM 1.4.05) | SERCOM, RA,S/MAR |  | 2025
1.5.02 | White Paper on requirements for Cryosphere Services developed to influence priorities for action across WMO constituent bodies and their activities/priorities |  | Development of a White Paper on Services relate to the Cryosphere | SERCOM, JET-Cryo, S/HWC, S/CS |  | 2026
3.1.03 | Critical gaps and emerging new research directions with regards to improved understanding of the Earth system identified to support DRR, agriculture, urban development, aviation, the energy sector, etc. |  | 28.5 WWRP: Integrated Prediction of Precipitation and Hydrology for Early Actions (InPRHA) | RB, SI/WWRP
3.2.01 | Models and tailored forecasting and prediction products developed for specific sectors (e.g. urban, aviation, health, agriculture, energy) enhancing/strengthening collaboration and engagement between natural and social scientists, stakeholders and users in support of attribution and adaptation
3.2.05 | Methodologies for impact-based forecasting improved through integration of socio-economic, cultural, and other relevant information